## Sheet1
Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
MCAL_EXTINT_Design | Bassel Yasser | done | 1 hour | 30 min
MCAL_EXTINT_Implementation | Bassel Yasser | done | 1 hour | 45 min
MCAL_EXTINT_Testing | Bassel Yasser | done | 15 min | 15 min
HAL_Ultrasonic_Design | Bassel Yasser | done | 1 hour | 1 hour
HAL_Ultrasonic_Implementation | Bassel Yasser | done | 1 hour | 3 hours
HAL_Ultrasonic_Testing | Bassel Yasser | done | 16 min | 15 min
HAL_EXTINT_Design | Bassel Yasser | done | 15 min | 30 min
HAL_EXTINT_Implementation | Bassel Yasser | done | 30 min | 30 min
HAL_EXTINT_Testing | Bassel Yasser | done | 17 min | 15 min
HAL_LCD_Design | Bassel Yasser | done | 1 hour | 45 min
HAL_LCD_Implementation | Bassel Yasser | done | 1 hour | 45 min
HAL_LCD_Testing | Bassel Yasser | done | 17 min | 15 min
MCAL_DIO | Mahmoud Adel | done | 17 min | 15 min
MCAL_TIMER | Mahmoud Adel | done | 1 hour | 45 min
HAL_PWM | Mahmoud Adel | done | 1 hour | 45 min
HAL_CAR_CONTROL | Mahmoud Adel | done | 1 hour | 1.5 hour
HAL_KEYPAD |  | done
HAL_TIMER_MANAGEMENT |  | done
APP_Design | TEAM | done | 1 hour | 1.5 hour
APP_Implmentation | TEAM | done | 2 hours | 6 hours
APP_Testing | TEAM | done | 1 hour | 30 mins